## Slide 1: Risk Management

## Slide 2: Agenda
Overview and Definition
Processes of Project Risk Management
- Risk Management Planning
- Risk Identification
- Qualitative Risk Analysis
- Quantitative Risk Analysis
- Risk Moniotoring and Control

## Slide 3: Risk Event
A discrete occurrence that may effect the project for better or worse.
- Can have positive outcomes (opportunities) or negative outcomes (risks).
Can be evaluated by combining its probability of occurrence with the value of the risk event.

## Slide 4: Project Risk Management
The systematic process of identifying, analyzing and responding to project risks.
- Maximizing the probability and consequences of positive events to project objectives.
- Minimizing the probability and consequences of adverse events to project objectives.
- Applied to all projects.
A function that aims at reducing uncertainty and damage.

## Slide 5: Why Project Risk Management?
Every project has risks
Changing business environment
Risky opportunities
Risky decisions
Past experience may not repeat

## Slide 6: Provides Visibility Since every projects has risks, we need a structured approach
Calibrates acceptable vs. unacceptable risks
Quantifies areas of uncertainty
- Partial or incomplete information
- Separates knowledge from opinion
- Examines objective vs. objective probabilities
Adapts to varying risk exposure

## Slide 7: Types of Risks- Varying Perspective
Corporate Business Management Perspective
- Business Risk
Objective : Maximize profits
Includes the inherent chances of both profit or loss associated with the business.
Organizations employ professionals to increase the chances of profit & reduce the chances of loss.
Pure (Insurable) Risk
Objective : Minimize losses

## Slide 8: Insurable Risks- Pure Risks
Direct Property Risk (Insurance against Assets)
- Auto collision, Fire, theft, flood, wind storm, ….
Indirect Property (Consequential) Risk
(Insurance Against Impacts on 3rd Parties)
Extra expenses associated with renting alternative temporary accommodation or equipment following its damage or destruction
Loss due to business interruption due to the unavailability of equipment replacement

## Slide 9: Insurable Risks- Pure Risks
Legal Liability (Insurance Against a Person Filing a Lawsuit .. Professional Protection)
- Design errors, project performance failure, personal injury or property damage against the contractor
Personal (Staff Protection )
- Staff bodily injury

## Slide 10: Types of Risks- Another Way
Known (Items or situations containing no uncertainty)
- Example : Death– It Will Happen & there is no uncertainty about it.
Known Unknowns (Exist but how do they affect us? )
- Example: Electricity Bill– We know we will get one next month, but we do not know how much it will be.
Unknown Unknowns (Neither know about them nor know about effects)
- Example : before the first case of AIDS existed, it was unknown unknown

## Slide 11: Project Risks
Project risks are in all project knowledge areas
Integration 5) Quality
Scope 6) Human Resource
Time 7) Procurement
Cost 8) communication

## Slide 12: Example of Risks- Project Management Perspective Many identifiable risks impact two or more areas. Do no double count
Scope Risks
- Risks associated with changes of scope, or the subsequent need for “fixes” to achieve the required technical deliverables
Quality Risks
- Failure to complete tasks to the required level of technical or quality performance

## Slide 13: Example of Risks- Project Management Perspective Many identifiable risks impact two or more areas. Do no double count
Schedule Risks
- Failure to complete tasks within the estimated time limits, or risks associated with dependency network logic.
Cost Risks
- Failure to complete tasks within the estimated budget allowances

## Slide 14: Summary of Risk Classification
Business risks vs. pure (insurable) risks
Classified by uncertainty
Classified by their nature
Classified by impact on project elements
Classified by their source

## Slide 15: Risk Management Planning
Is the process of deciding how to approach and plan the risk management activities for a project.
Plan for the Risk management Processes- to ensure level, type and visibility of risk management are commensurate with both the risks and importance of the project to the organization.

## Slide 16: Risks Management Planning
Inputs | Tools and Tech | Outputs
1. Project Charter | Planning meetings | Risk Management Plan
2. Organization’s risks management policies |  | 
3.Defined roles & responsibilities |  | 
4. Stakeholder risk tolerances |  | 
5. Template for the organization's |  | 
6. WBS |  | 

## Slide 17: Risk Management Planning - Inputs
Organization’s risk management policies
- Some organizations may have predefined approaches to risk analysis and response that have to be tailored to a particular project.
Defined roles & responsibilities
- Predefined roles, responsibilities, and authority levels for decisions making will influence planning
Template for the organization’s risk management plan
Some organizations have developed templates( or pro-forma standard) for use by the project team.
The organization will continuously improve the template, based on the application and usefulness in the project

## Slide 18: Risk Management Planning- Inputs
Stakeholder risk tolerances
- Different organization & different individuals have different tolerances for risk.
Expressed in policy statements or revealed actions
Utility Theory- Formalizes management’s risk views to explain its tolerance for risk (useful in decision tree analysis)
Risk Neutral
Risk Indifferent
Risk Seeker/Lover
(Risk Acceptance)
Increasing Rate)
Risk Averter/Avoider
(Low tolerance for risk)
(Risk Aversion) (Decreasing Rate)
Attitude towards risk
Investment
Time

## Slide 19: Risk Management Planning- Outputs
Risk Management Plan
Describes how risk identification, qualitative and quantitative analysis, response planning, monitoring and control will be structures and performed during the project life cycle.
Does not address response to individual risks
Includes
Methodlogy |